## Sheet1
Project | Cost | Lead | $ | Comments | Outcome
Upstream Migration / Straying Avoidance
KLOG Fix |  | Lewis Bair | X | DWR working with RD 108 to install slip clutch to hoist assembly to prevent structural failure. Project planned start this fall, finish in spring. Work will likely occur in spring 2020.
Tisdale Bypass Management Plan |  | DWR, RD 1500 |  | DWR lead on adult fish passage project. RD 1500 is lead on juvenile passage/habitat project.
Egg Incubation -- 2017 Operations for Temp Management
Shasta temperature probes and data loggers (meteorological station) | $50,000 to $125,000 | Mike Deas, Josh Israel | X | Up-reservoir conditions monitored including the Sacramento, McCloud and Pit River arms. Determined that temperature at specific depths remains constant even as you move away from the dam.
Improve modelling tools to predict temperature resources/model temperature operations | > $500,000 | Mike Deas, Jeff Reiker | X | Workign with BOR on inputs to the model. Includes leakage at TCD. Working on lose ends. Documentation due to be out in mid-to-late August
CV heat budget (the watershed-reservoir component) to simulate inputs into Shasta Reservoir over the current season and through long-term climate change scenarios | ~ $100,000 | Eric Danner |  | Working model developed for flows into Shasta. Ready to present soon. Temperature is good. Working on flow accuracy.
Disease impacts study on winter-run juvenile Chinook salmon | 54000 | Jim Smith | X | Considering study in upper river in future drought years and in lower river when temperature is likely warmer.
Improved Spawning Habitat
Place gravel in the Sacramento River to create functional spawning habitat upstream of the Highway 44 Bridge | ? | John Hannon |  | Market Street done. Keswick starting at the end of July.
Stockpiling new gravel for future placement | ? | John Hannon |  | Trying to utilize excavated materal on-site
Emerging Juvenile Fry and Smolts
Drift invertebrate (salmon prey) camera system to measure available food for juvenile salmon | < $150,000 | Eric Danner |  | Project is in a holding pattern.
Side-channel -- Cypress Ave. Bridge downstream project | 400000 | Thad Bettner | X | TU working with Redding to implement without bridge requirement. Building/funding bridges over side channel still an issue. John Hannon is working on it.
Look for an opportunity to expedite floodplain reconnection projects on lower Battle Creek (Rancho Brisgow) | ? | Ruth Goodfield |  | Side channel project that is stalled due to land ownership dispute
Side-channel projects in Tehama and Shasta Counties | ? | John Hannon, Harmony Gugino | X | Rio Vista -- RD 108 construction. Anderson River Park -- ready to go in fall. Need construction lead. Reading Island -- work being done right now; lower channel this fall. East Sand Slough -- need to lower utilities that are burried 2 to 3 feet lower. Kapusta Island -- vegetation survey conducted. Shea Island -- DWR land survey conducted.
Out-migrating Salmon
Implement new monitoring projects of stressors closer to spawning grounds | $100,000 + monitoring | Jason Roberts |  | CVPIA Charter drafted for FY19. Group identified top projects. Checking to see if it needs funding.
Spot monitoring for salmon during episodic high flow, high turbidity events | 100000 | Jim Smith | X | Expecting considerable out-migrating juvenile winter-run. Best carcass survey since 2006.
Bureau of Reclamaion and Sacramento River Settlement Contractors coordination to provide Sacramento River spring pulse flows to benefit wild and hatchery salmon; NMFS will be monitoring | $344,000 (monitoring) | Jeff Reiker, Howard Brown, Matt Johnson | X | Posponed a year -- implementation in 2020. Acoustic receiver in GCID oxbow to determine entrained fish.
Food for Fish Program |  | Lewis Bair, Jacob Katz | X | Third year of pilot study completed. Tracked ability for fish to feed in the river. Even with high flows there was good response. Report to be completed once grant fundign is acquired.
Fish/Rice Project | $1,200,000 - 1,300,000 | Paul Buttner | x | Impacted by bypass flooding. Survivability not good. For this winter the study will split fish between wet side and dry side fields. Dry side fish will move to wet side to volitionally pass.
Food Web Project |  |  |  | Food for smelt in the north Delta. Led by DWR. Report available later in 2019. Will be conducted again in early September. Model depicting how water from drained rice moves through the Delta during the program has been developed.
Willow Bend |  | River Partners | X | Construction in summer 2019. Pilot Project; Includes control structure.
Completed Projects:
Construction of Wallace Weir Fish Rescue Facility | 13300000 | Lewis Bair | X | Project Completed. RD 108 to turn over the project to DWR in 2019
Market Street gravel project | 350000 | Thad Bettner | X | Completed in 2016
Install refugia to reduce predation of emerged salmon (i.e. RGF pilot project) | 400000 | Roger Cornwell | X | Completed in May 2017. Monitoring for next three years. | Video from monitoring: https://youtu.be/-n5IQ4eDO4s
Side-channel -- Cypress Ave. Bridge upstream project | 400000 | Thad Bettner | X | Repaired damage from high flows
Habitat/redd monitoring in upper Sacramento River | 35000 | Dave Vogel |  | Completed in 2017
"Don't Tred on my Redd" signs | 1200 | Jason Roberts | X | Signs installed
Lake California Side Channel Project |  | Lewis Bair | X | Project completed 12/17
Kutras Lake project -- woody material installed on banks | ? | John Hannon | X | Local TU Chapter is project champion.
Kapusta 1a Side Channel |  |  | X | Western Shasta RCD
Sacramento River bathymetry to improve flow model from Shasta to RBDD | ~ $125,000 | Jason Roberts, Eric Danner | X | The lidar flight work completed. The data in available. | Looking to extend from RBDD to Tehama Bridge
CSU Chico predator study from Hamilton City and Colusa | 12000 | Todd Manley | X | Project completed. Thesis submitted.
Fremont Weir Adult Fish Passage Modification Project |  |  | X | Construction completed